## Sheet1
Task Name
Advanced Analytics Project
Project Kickoff
Business Understanding
Define Objectives
Identify the key business variables
Define Project Goals
Define project team
Define success metrics
Identify Data Sources
Data Sources Documented
Data Dictionaries Delivered
Charter Document Delivered
Data Acquisition and Understanding
Ingest the data
Explore the data
Set up data pipeline
Deliver Data Quality Report
Deliver a Solution Architecture
Checkpoint Decision
Modeling
Feature Engineering
Train Model
Evaluate Model
Define Feature Sets
Create Model Report
Checkpoint Decision
Deployment
Operationalize the Model
Deliver status dashboard
Deliver final modeling report
Deliver Final solution architecture document
Customer Handoff
System Validation
Project Handoff
Project Close-out: Exit Report of Project for Customer